## Sheet1
Category | Item | Status
Phase 1: Internal Toolkit | Compliance Automation Micro-SaaS | In Progress
Phase 1: Internal Toolkit | OneDrive/SP Folder Structure Enforcer | Not Started
Phase 1: Internal Toolkit | Secure External Sharing Tracker | Not Started
Phase 1: Internal Toolkit | Vault365 Compliance Engine Bundle | Not Started
Phase 2: Productised Services | M365 Reset + Automation Jumpstart | Planned
Phase 2: Productised Services | Virtual CTO-as-a-Service | Planned
Phase 2: Productised Services | Tenant-Wide Audit & Security Assessment | Planned
Phase 3: Passive Income Layer | AI-Automated M365 Learning Hub | Not Started
Phase 3: Passive Income Layer | Premium Azure Templates & Architecture Packs | Planned
Phase 3: Passive Income Layer | YouTube + Newsletter + Blog | Planned
Phase 4: Recurring Revenue Products | Power Automate Templates Marketplace Seller | Not Started
Phase 4: Recurring Revenue Products | Copilot for M365 Admins | Not Started
Phase 4: Recurring Revenue Products | AI Retention Labeller / Classifier | Not Started
Foundational Tools | Vault365 Deployment Toolkit | Completed
Foundational Tools | Graph API Credential Manager | In Progress
Foundational Tools | PnP Automation Dashboard | Planned
Operational Launch Plan | Week 1: GitHub repo + toolkit stubs | Completed
Operational Launch Plan | Week 2: First Automation Product | In Progress
Operational Launch Plan | Week 3: SharePoint Public Hub + Blog | Not Started
Operational Launch Plan | Week 4: Substack + Newsletter | Planned
Operational Launch Plan | Week 5: Gumroad Product Launch | Planned
Operational Launch Plan | Week 6: YouTube + ConvertKit Setup | Planned
Branding & Licensing | Branding Assets + Slogan | In Progress
Branding & Licensing | Blog + Newsletter | Planned
Branding & Licensing | Governance, IP, Licensing | Planned